## Sheet1
www.goodoldmanoj.com
Burn down chart
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project |  | Construct DB tables | 12 | 6 | 6
My Project | Product | Create java product class | 6
My Project | Shopping | Create java shopping class | 6
My Project | User | Create java user class | 8
My Project | Staff | Create java staff class
My Project | Category | create java category class
My Project | EditOrders | Construct java for making orders
My Project | EditUsers | Construct java edit users
My Project | EditCategory | Construct java edit category
My Project | EditProducts | Construct java edit products
My Project | EditBiProd | Connect products category bindings
My Project
My Project
Ideal - Remaining efforts in uninterrupted working hours |  |  | 32 | 28.8 | 25.6 | 22.4 | 19.2 | 16 | 12.8 | 9.6 | 6.4 | 3.2 | 4.4409e-15
Actual - Remaining efforts in uninterrupted working hours |  |  | 12 | 6 | 6
Note on F5: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered
Note on G5: Remaining effort as of that day to complete the task.It's NOT last day effort - hours worked. So this can go up if new challenges got uncovered